## Slide 1: Commonwealth Fencing Championships 2022 Update
20 January 2022

## Slide 2: Purpose
To provide an update on the Board’s approach to participation in the 2022 Commonwealth Fencing Championships.
To facilitate an open question and answer session with you

## Slide 3: Background
Last October the Fencing New Zealand (FeNZ) Board confirmed its approach to NZ’s participation in the Commonwealth Fencing Championships which is scheduled to be held in London, 8-20 August 2022.
The inclusion of Cadet, Junior, Senior and Veteran events, together with the issues generated by COVID-19, create some unique challenges for FeNZ to address when planning for NZ participation.
At the heart of our approach is the duty of care the Board has for the health & safety of our members.
The Board’s commitment to sanctioning participation by a managed team is, therefore, contingent on:
  An acceptable risk assessment
  The adoption of appropriate tour risk management protocols
  A clear understanding that while the Board can put in place measures to mitigate and manage risk it can not entirely eliminate it. Accordingly, if a decision is made to send a managed team, team members will need to make an informed decision to accept that risk.
While we are progressing arrangements to enable participation, the Board will make a final decision on whether or not to send a team in early May.

## Slide 4: Progress to date
Project Plan established to guide our approach
Board has committed $15,000 to support NZ team participation
Selection policy approved
2022 National competition & training camp programme tailored to support selection and build up to Commonwealths
Athlete longlist & training plans established
Appointment and compensation arrangements for team managers & coaches agreed
Preliminary athlete cost estimates established
Call for applications for team management and coaching positions
Engagement with Commonwealth Fencing Federation and CFC2022 Organising Committee
Engagement with Sport NZ & NZ Olympic Committee
Availability of suitable insurance cover being investigated
Preliminary planning for sponsorship/fundraising applications underway
Key documents available on the FeNZ website: https://www.fencing.org.nz/resources/documents/commonwealth-fencing-championships-2022-documents

## Slide 5: Risk Assessment
The Board’s Covid Committee will undertake the risk assessment and provide its advice to the Board for its consideration and final decision. Our approach will reflect Sport NZ guidelines for international travel for NZ high performance sports.
The assessment will take account of the benefits and risks associated with participation. Ultimately it needs to determine whether the benefits are commensurate with the known and potential risks and that the proposed risk management arrangements provide reasonable assurance that those risks are acceptable in terms of the Board’s duty of care for participant health and wellbeing.
Key considerations are expected to include:
  Competition Benefits:
    Will the Championships be at a level and standard similar to previous events?
    Will the Championships deliver an appropriate competitive challenge for NZ fencers?
  In-country risk assessment:
    What is the current and projected Covid-19 epidemiology in London (cf. NZ)?
    Does the national health service have the capability and capacity to manage the current and anticipated Covid cases?
    Will team members have access to, appropriate healthcare support?
    Have appropriate Covid risk management protocols been established by the UK government and the CFFC2022 Organising Committee commensurate with the risk?
  NZ team risk management:
    Is suitable travel insurance available for team members to support Covid-related medical and logistics issues?
    Are team members assured of return access to New Zealand at the end of the competition?
    Has FeNZ established, or is it able to establish, appropriate Covid risk management arrangements that satisfy the Board’s health and safety obligations to the team and comply with UK, NZ government and CFFC22 organising committee requirements?
    Can the FeNZ Board provide the information required for potential team members to make an informed decision about the risks associated with participating in the competition?
In practical terms if team members cannot secure return access to NZ and access to appropriate travel insurance it is highly unlikely that the FeNZ Board could support a managed tour.
There may, however, be circumstances where the Board may still permit individual athletes that meet is selection criteria to compete at their own risk being fully aware of it’s adverse risk assessment.

## Slide 6: Participation Requirements
We are committed to establishing appropriate risk management arrangements, which will include a tour participation agreement.
This is expected to include:
  Compliance with the FeNZ Code of Conduct
  Full vaccination and travel insurance cover
  Compliance with NZ Government, Host Government and CFCC organising committee health and safety requirements including any Managed Isolation & Quarantine (MIQ)
  Compliance with any additional health and safety protocols that may be established by the FeNZ Covid committee,
  Accompanied travel by parent or designated adult responsible for athlete welfare pre & post competition period for all under 18-year-old athletes
  Acceptance of a FeNZ disclaimer acknowledging that athletes are travelling at their own risk.
We also anticipate establishing contingency plans to address pre-tour, on-tour, and post-tour Covid-related risks, including arrangements that will apply in the event of team member(s) testing positive, or changes to government Covid mitigation policies.

## Slide 7: Event Entry Limits
Entry Limits: The selectors may name up to 5 fencers for each individual and team event at Commonwealths (with the exception of veterans individual and team events where there is no entry limit on individual entries and additional teams will be able to enter supplementary ‘challenge’ events).
Team Selection: Where selectors have identified 5 eligible fencers for a team event, the Team manager must nominate a final team of 3 or 4 fencers not later than 24 hours before the start of the event.
Vets Team Challenge: For veterans team challenge events there is no limit on the number of teams entering. The organisers will accept team entries up until 3pm two days before each challenge event. The organisers will also be accept teams comprising individuals from different countries, to maximise the opportunity for participation in these events.

## Slide 8: NZ Selection Policy (Summary)
Selection will be based on the following order of priority:
The top ranked fencer from the FeNZ rankings in each event at the closure of the selection period (subject to terms & conditions outlined below)
The winner of an approved designated trial event (subject to the terms & conditions outlined below)
Those fencers who, based on performance, experience, skills, fitness and form, the Selectors believe will make the greatest contribution to the likelihood of winning medals in a teams event.
Those fencers who, based on performance, experience, skills, fitness and form, the Selectors believe will provide the greatest likelihood of winning medals in an individual event.
Minimum Selection Criteria:
A demonstrated level of performance, experience and skills the Selectors believe will make a top half finish a minimum likely outcome.
Assessment of performance, experience and skills are the sole preserve of the Selectors. The assessment will include but not be limited to: training plans and adherence to them, fencers results both recent and pre-Covid impacted, depth of previous competition experience, attitude and performance at any training camps or trials.
Fencers competing or resident outside of New Zealand must submit results and other equivalent material with any final nomination.
Fencers are expected to attend the two designated training camps and the designated trial event.
Fencers who are resident overseas and for whom attendance is not feasible may request exemption from some or all of this requirement.
Automatic selection based on winning a trial event is subject to there being at least 8 entries in the event, the selectors being satisfied the standard is representative of the highest level of fencing in NZ for that event and that the minimum selection criteria outlined above are met.
The ‘top ranked fencer’ refers to the fencer ranked number 1 in the FeNZ rankings, not the top ranked member of the longlist.
Except under exceptional circumstances selections will be made exclusively from those who have nominated to the longlist
The full selection policy is available on the FeNZ website: https://www.fencing.org.nz/resources/documents/commonwealth-fencing-championships-2022-documents/131-selectionpolicy-cc2022-final/file

## Slide 9: Athlete costs – preliminary estimate
The following table presents very preliminary estimates. They will be refined over the coming months as we gain further clarity around a range of issues including – travel costs, accommodation options & costs, insurance, and Covid mitigation requirements.
ATHLETE TOUR COST PROVISIONAL ESTIMATE |  |  |  | 
 | Scenario 1 | Scenario 2 |  | 
Estimated Costs Payable to FeNZ | 8 Nights/8 days | 12 nights/12 Days |  | Assumes 1 day travel + 5 days in UK pre-comp + 3 or 7 days for events + 1 day travel
Athlete Levy | $960 | $960 |  | Total staff costs included in the athlete levy divided by estimated number of fencers only. No adjustment yet made for fencers using coach or management services for different periods of time. Based on estimated staff costs, and a staff to athlete ratio of 1:9 (5.5 mgr/coaching roles to 50 athletes). Includes FeNZ Nomination Fee for overseas events of $150. Cost reduces if more fencers (e.g. to $800 if 60 fencers). Cost increases if fewer fencers (e.g. $1,134 if 45).
Team Tracksuit & T-Shirt | $150 | $150 |  | Based on Canterbury Sports Tracksuit Jacket @ $89 + Pants @ $60. Costing only. Uniform provider not yet selected
FIE Licence Fee | $70 | $70 |  | 
Tournament Entry | $180 | $360 |  | Based on 1 & 2 individual weapon @ GBP95 ea. Team entries covered by FeNZ.
Sub-Total: | $1,360 | $1,540 |  | No sponsorship or fundraising discounts included
Additional Estimated Athlete Costs |  |  |  | 
Insurance | $230 | $250 |  | Covermore Travel Insurance (subject to Govt Travel Advisory 'do not travel' being lifted)
Airfares | $2,700 | $2,700 |  | AirNZ Economy (Lowest fares as at 16 Jan 2021 $2661).
Covid Pre-departure & arrival tests | $522 | $522 |  | Assumes $250 (departing NZ) + $136 x 2 (UK arrival and departure).
Airport Transfers | $50 | $50 |  | Tube or shared shuttle
Accomodation | $608 | $912 |  | Based on 7 or 11 Nights twin share @ Ibis budget(no-share is double cost). Not actual accommodation. Selected for costing purposes only. May be less if UEL accommodation secured.
Expenses | $1,000 | $1,500 |  | 8 or 12 days @ $125 (meals x 3 + tube pass, daily Covid tests & incidentals). May be less if UEL accommodation package with meals secured.
Managed Isolation (if required) | $0 | $0 |  | Assumes home isolation - no provision for daily expenses
Sub-Total: | $5,110 | $5,934 |  | No sponsorship or fundraising discounts included
TOTAL ESTIMATED COSTS: | $6,470 | $7,474 |  | Does not include accompanying parent/guardian costs for U18s

## Slide 10: Recent CFFC22 Organising Committee Advice
Accommodation: University of East London accommodation packages in 4-6 person apartments walking distance from venue to be made available to visiting teams with priority given to Cadets & Juniors for the period of their competition events. We will explore obtaining this accommodation for the whole team and for a longer period.
Training: 4 day training camp to be held at the competition venue ending 2 days before the first day of competition. Arrangements for visiting teams to fence at London clubs also being negotiated.
CFFC22 Covid Risk Management Requirements: Final Protocols to be published 1 Aug. Will apply the stricter approach out of:
FIE World Champ requirements
UK Government guidelines
British/England Fencing Covid regulations.
It is expected that participants will require proof of vaccination or a PCR test no more than 72 hours old + negative daily lateral flow tests. UK govt protocols to be followed for positive tests, including 10 days quarantine.

## Slide 11: Next Steps
Selected Key Milestones | Target Date
Applications for Team Manager close | 30 Jan 2022
Waitangi Weekend National Competition (Wellington) | 5-7 Feb 2022
Applications for team coaching positions close | 13 Feb 2022
Sponsorship/grant applications | 28 Feb 2022
Call for athlete nominations issued | 1 Mar 2022
South Island Champs (Christchurch) | 18-19 Mar 2022
Athlete nominations close | 31 Mar 2022
FeNZ Carnival – National Trials (Auckland) | 15-18 Apr 2022
Participation risk assessment completed by FeNZ Covid Committee | 25 Apr 2022
Board decision on managed team participation & ratification of selections | 1 May
Athletes advised of tour status & selection decisions (including reserves) | Early May 2022
Athlete acceptance, participation agreement & payment of fees | 18 May 2022
Management & coaching appointments for tour phase confirmed | 20 May 2022

## Slide 12: Appendix A
Participants | Selection (Ind. & Team) | FIE License & Entries | Flights | Designated Team Accommodation | Uniforms (Tracksuit/ T-shirt) | FeNZ requirements | CFC/Host Country Req. | NZ Govt Req (eg. MIQ) | Comment
Cadets & Jnrs | Yes | Yes – via FeNZ | Book own flights inform FeNZ | Required (booked via FeNZ) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Accompanied/ under care of designated adult (U 18s) Tour Levy | Yes – as required | Yes – as required | All U18 year olds to be accompanied by parent/ designated adult responsible for welfare pre and post competition period. Assume athletes at team accom min. 2 days before first event
Seniors | Yes | Yes – via FeNZ | Book own flights inform FeNZ | Required (booked via FeNZ for team accommodation) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Tour Levy | Yes – as required | Yes – as required | Assume athletes at team accommodation min. 2 days before first event
Veterans | Team only | Yes : Direct entries with CFFC. Team entries via FeNZ | Book own flights inform FeNZ | Preferred (booked via FeNZ for team accommodation) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Tour Levy | Yes – as required | Yes – as required | Assume athletes at team accomodation min 2 days before first event
Team Manager | To be appointed by FeNZ | n/a | Book own flights with FeNZ agreement | Required (booked via FeNZ) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Coach Code of Conduct | Yes – as required | Yes – as required | May need to assist with coaching depending on size of tour party. Assumes coverage of Vet & Senior team mgt responsibilities.
Manager (Cadets & Jnrs)* *If numbers require | To be appointed by FeNZ (if req) | n/a | Book own flights with FeNZ agreement | Required (booked via FeNZ) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Code of Conduct | Yes – as required | Yes – as required | Focus on Cadet/Jnr team mgt, but may deputise for DdM. May be accompanying parent.
Team Coaches | To be appointed by FeNZ | n/a | Book own flights with FeNZ agreement | Required (booked via FeNZ) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Coach Code of Conduct | Yes – as required | Yes – as required | Number dependant on size of team. Need to cover all weapons.
Personal Coaches | N/a. But FeNZ NZ Squad Coaching Policy applies. Written consent from FeNZ to join team required | n/a | Book own flights inform FeNZ | Preferred (booked via FeNZ if team accommodation option requested) | Yes | Vaccination Travel Insurance Participation agreement & personal information sheet Coach Code of Conduct | Yes – as required | Yes – as required | Costs to be met by personal coaches’ athletes who must still contribute to wider team mgt and coach costs through the athlete tour levy
Accompanying Parents | N/a. | n/a | Book own flights inform FeNZ | Available booked via FeNZ if team accommodation requested | N/a | Vaccination Travel Insurance | Yes – as required | Yes – as required | 
Preliminary Overview of Tour Party Requirements